## Slide 1: AN AGILE DEVELOPMENT METHODOLOGY
Tuesday, February 18, 2014
The Sprint Activities Schedule
The Sprint Activities Schedule
The Agile Process Team
Brad Huett Don Kasner
Megan Schmid Dave Latham
Erich Villasis Steven Hill
Siva Natarajan Bryce Budd

## Slide 2: What are Sprint Activities?
The Agile Sprint has three types of activities that are performed within the ten day period:
The Iteration Cycle: A Ten Business Day Activities Plan
The Sprint Activities Schedule helps define and clarify the activities that a given Agile Role has on any given day of the iteration.
Current Sprint Activities
Previous Sprint Activities
Next Sprint Activities
The activities are labeled as Day 1 through Day 10. Most days have activities that span two types.

## Slide 3: What are Week One Activities?
Week 1 of the Agile Sprint
Sprint | Mon-Day 1 | Tue-Day 2 | Wed-Day 3 | Thu-Day 4 | Fri-Day 5
Previous Sprint | PO & BA: Demo Certification and “Dress Rehearsal” QA & Architect: Demo Validation Support Developers: Code Migration, Demo Validation, and troubleshoot Execution Issues | Team: Sprint Demo Product Demonstration Team: Sprint Retrospective Meeting |  |  | 
Next Sprint Planning |  |  |  |  | PO, BA & QA: Select and Prioritize next sprint candidate stories. Initial creation of test data and test cases.
Current Sprint | New Sprint Kickoff Team: Stand Ups QA: Smoke Test QA environment, Validate Daily Builds Architect: Dev Support Developers: Coding, Daily Builds & Push to QA, Code Review, Enter Time in JIRA | Team: Stand Ups QA: Testing, Validate Daily Builds Architect: Dev Support Developers: Coding, Daily Builds & Push to QA, Enter Time in JIRA | Team: Stand Ups QA: Testing, Validate Daily Builds Architect: Dev Support Developers: Coding, Daily Builds & Push to QA, Code Review, Enter Time in JIRA | Team: Stand Ups QA: Testing, Validate Daily Builds Architect: Dev Support Developers: Coding, Daily Builds & Push to QA, Code Review, Enter Time in JIRA | Team: Stand Ups QA: Testing, Validate Daily Builds Architect: Dev Support Developers: Coding, Daily Builds & Push to QA, Code Review, Enter Time in JIRA

## Slide 4: What are Week TwoActivities?
Week 2 of the Agile Sprint
Sprint | Mon-Day 6 | Tue-Day 7 | Wed-Day 8 | Thu-Day 9 | Fri-Day 10
Previous Sprint |  |  |  |  | 
Next Sprint Planning | PO & BA: Groom next sprint candidate stories. QA: Create use cases, test data, test suite for selected sprint candidate stories. Architect & Lead Developers: Analysis of selected next candidate stories. | Architect: Review & Certify Initial Design for next Sprint candidate stories. Lead Developers: SpecFlow Feature Stories for next Sprint candidates & create Initial Design Document for next Sprint candidate stories. QA: Validate, Create Test Cases and Data for next Sprint Candidate stories as the initial Developer’s QA Objective. | Team: Begin Next Sprint Planning Sessions: - Poker Planning, - Acceptance Criteria, - Team Capacity, - Task Acceptance Validate the QA Objective as defined by the initial QA Test Suites | Team: Continue Next Sprint Planning Sessions: - Poker Planning, - Acceptance Criteria, - Team Capacity, - Task Acceptance If Required | Team: Continue Next Sprint Planning Sessions (Validation, Poker Planning, Acceptance Criteria, Team Capacity, Task Acceptance) If Required
Current Sprint | Team: Stand Ups QA: Testing, Validate Daily Builds Architect: Dev Support Developers: Coding, Daily Builds & Push to QA, Code Review, Enter Time in JIRA | Team: Stand Ups QA: Testing, Validate Daily Builds Architect: Dev Support Developers: Coding, Daily Builds & Push to QA, Code Review, Enter Time in JIRA | Team: Stand Ups QA: Testing, Validate Daily Builds Architect: Dev Support Developers: Coding, Daily Builds & Push to QA, Code Review, Enter Time in JIRA | Team: Stand Ups QA: Testing, Validate Daily Builds Architect: Dev Support Developers: Coding, Technical Debt & Bug fixes, Daily Builds & Push to QA, Code Review, Enter Time in JIRA | Team: Stand Ups PO & BA: Demo Planning QA: Testing, Validate Daily Builds, Final Demo Testing, Integration Support Architect: Demo and Integration Support Developers: Coding, Daily Builds & Push to QA before 12:00 Code Freeze, Code Review, Code Freeze at 12:00PM, Push to Demo Environment, Enter Time in JIRA

## Slide 5: In Conclusion: Sprint Activities Schedule
Change is hard for most people. Our comfort zones protect us from harm in our minds. This is a false sense of protection.
Understanding the Sprint Process
The Sprint Activities Schedule is a Short-term “Cheat Sheet” that adds Process Clarity to the Changing Environment
As a working team we need clarity and comfort in our roles and responsibilities
In the transition stages of change we need a “Security Blanket”. The Sprint Activities Schedule is the blanket. It life span is generally very short as the Sprint daily activities become second nature very quickly